## Slide 1: GC0104 Proposal EU Connection Codes GB Implementation – Demand Connection Code
Grid Code Review Panel
16th August 2017

## Slide 2: Objective and Defect
  Objective: Comply with legally binding decisions of the European Commission and/or the Agency
    DCC is one of the three European Connection Codes and needs to be implemented in GB by September 2018.
  Defect: GC0091 Work Group identified requirements in DCC that either don’t currently exist in the Grid Code or there are conflicting requirements in the Grid Code.

## Slide 3: Solution
  GC0104 will use the code mapping produced in GC0091 to identify and implement the specific requirements from DCC into the Grid Code to be compliant with EU law.

## Slide 4: Code Administrator
Chrissie Brown
16/08/2017

## Slide 5: Code Administrator Proposed Progression
The Panel is asked to agree:
This modification should:
  be assessed by a Workgroup and where these discussions should be held:
    Workgroup day
    Separate Workgroup
  Terms of Reference for the Workgroup

## Slide 6: Proposed Timeline
Milestones | Dates
Workgroup Meeting 1 - technical requirements on transmission-connect demand facilities | September 2017
Workgroup Meeting 2 - technical requirements on facilities providing demand-side response | October 2017
Workgroup Meeting 3 - alternative proposals and final run-through of workgroup report | November 2017
Workgroup Consultation (15 Working days) | November 2017
Workgroup Meeting 4 | December 2017
Workgroup Report presented to Panel | January 2018
Code Administration Consultation Report issued to the Industry | January 2018
Draft Final Modification Report presented to Panel | February 2018
Modification Panel Recommendation vote | February 2018
Final Modification Report issued the Authority | March 2018
Authority decision | April 2018
Decision implemented in Grid Code | May 2018