## All Actions
Action Log: Meeting 11
Meeting Name: GC0048: Joint GCRP/DCRP Workgroup on National Application of RfG
| Action | Owner | Progress | Status
1 | Investigate whether BELLAs/BEGAs will still exist in the future | RW | Update 24/9/14: RW advised they will still exist and noted that RfG doesn’t change the contractual relationships between parties. | Closed
2 | Workgroup to provide comments on Terms of Reference before finalising at the next GCRP/DCRP | ALL | Action complete. Noting that as with any Terms of Reference, they are ‘live’ working documents and therefore may be subject to change in the future. | Closed
5a | Requirements for GB parties (Generators, Network Operators etc.) to ensure compliance with the European Network Codes once they enter into force. An non-compliance consequences. (Monitoring of this compliance is actioned by DECC and Ofgem) | Ofgem and DECC | Update 20.10.14 - Action 5 split into two sections based on workgroup feedback. This action is for more clarity on the requirements as and when available from Ofgem/DECC. Updated 20.11.14 - Taken forward with action 5b and action 9 into new action 25. | Closed
5b | Requirements for Member State Compliance with the European Network Codes once they enter into force/implementation monitoring. (Monitoring of this would be actioned by ACER and ENTSO-E). | Ofgem and DECC | Update 20.10.14 - Action 5 split into two sections based on workgroup feedback. This action is for more clarity on the requirements as and when available from Ofgem/DECC. Updated 20.11.14 - Taken forward with action 5a and action 9 into new action 25. | Closed
6 | Update the comparison table between RfG and the existing GB Codes | AJ | To confirm timescales - could draft based on 'non-yellow' articles in the January 2014 RfG code, or could wait for next RfG Commission draft. Update 20.10.14 - Updated version discussed by AJ (Agenda item 5) | Closed
8 | Set out the process for making future changes to European Network Codes. | RM | There is a draft process set out by ACER. But in effect it requires the code to go back through Comitology which is therefore not quick. More clarity on this would be useful. Update 24.09.14 - Noted that this is a process to be defined and set by the Commission. RM to confirm if the 5 year period of changes to ENC once in force has a timetable, process or breakdown of what is covered. Update 20.10.14 - RM directed workgroup to the document published by ACER for how amendments can be made once an ENC becomes law. SLK circulated the link to the workgroup and included in the Meeting 4 minutes. | Closed
9 | Enforcement of G83 and G59 | RM | Check with DECC with regards to the enforcement of G83 and G59 and report back to RfG workgroup. Update 20.10.14 - RM advised that DECC and Ofgem are liaising on this and RM will report back to the workgroup on the outcome of these discussions. Updated 20.11.14 - Taken forward with action 5a and 5b into new action 25. | Closed
10 | FRT Requirements | AJ | Discuss at the FRT Workgroup the FRT requirements for Type B and how this fits in with ongoing GB work. Update 20.10.14 - Covered in presentation by AJ. | Closed
11 | Treatment of User’s under the GB Code framework | AJ | Provide an update slide on the treatment of User’s under the GB Code framework including BCA’s, BELLA’s, BEGA’s and LEEMPS. Update 20.10.14 - Covered in presentation by AJ. | Closed
12 | Examples of definition conflicts between ENC and GB codes | AF/All | Provide RM with examples of where definitions between ENC and GB codes conflict. In particular, the example given in the meeting of Power Stations and Units where the definitions will have to apply to existing plants. Update 20.10.14 - Examples provided and discussed by the workgroup. Update 20.11.14 - Taken forward within action 19. | Closed
13 | RfG timescales within connection offer documentation | AJ | Speak to legal to consider including a note within the informal offer letter or in the offer appendices referencing RfG and the likely timescales. Update 20.10.14 - Update provided by AJ of suggested options, AJ to consider and develop further with NGET Lawyers. Update 20.11.14 - Discussion ongoing within NGET. Update following December and January's workgroup meetings - AJ has discussed this internally at NGET, next steps are dependant on the pending new draft of RfG, therefore this action will be ongoing until such time. Update 19.03.15 Communicated through Customer Seminars held in March. Watching Brief being kept. | Ongoing
14 | Draft task list/project plan | CG and RW | Draft a timeline/project plan, tasks and prioritise and to send to the RfG workgroup ahead of the next meeting. Update 20.10.14 - Presentation covered by RW (Agenda item 7). Next steps; 1. RW and CG to produce task list which will be used to develop an RfG project plan. 2. Project plan lead by CG based on assumption of Entry into Force Q1 next year with an implementation of 2 years. This is to be included on the agenda for the next meeting. Updated 20.11.14 - Work ongoing, presentations covered under this months meeting agenda. Update 16/12/14 - Ongoing To be covered in Meeting 6 presentation material (Agenda Item 8). Update 20.01.15 - Action closed and 'RfG Project Plan' added as a Standing Agenda item. | Closed
15 | National Parameters Table | RM & AJ | Prepare a table outlining the national parameters to be selected following receipt of the list of actions under Articles 8 to 23 of the RfG code (January 2014 draft) from RM. This will incorporate the draft implementation plan presented to the ECCAF Code Mapping Working Group in April 2014. Update 20.10.14 - Presentation covered by RW (Agenda item 6) | Closed
16 | Assumptions Log to capture assumptions made to date in terms of implementation of RfG and to facilitate project plan. | CG | Covered in Meeting 5 presentation material. | Closed
17 | Insights from Commercial Frameworks-Gas rep from NGET on approach adopted on the Gas ENCs | RW | Covered in Meeting 5 presentation material. | Closed
18 | Ofgem/DECC Steering Group clarification. (Terms of Reference and the reporting lines requirement for the RfG workgroup) | RM | RM covered under A.O.B of Meeting 5. Specifics around how and what the RfG workgroup should report into the Steering Group still to be defined. RM to provide further update at December RfG workgroup meeting. As this item will now be covered as a standing agenda item, the action has been closed and covered as an agenda item going forward. | Closed
19 | Raise with ACER the definitions across ENCS and flag the codes which do not apply retrospectively | RM | Work is ongoing, RM to report back to the workgroup the progress made on this. Update 19.05.15 - Closed, RM has raised with Commission awaiting updates through next code versions. | Closed
20 | RW to prepare material for the three priority items to work through for the next workgroup meeting; Retrospectivity process (3.a.3) TSO setting of banding thresholds (3.b.2-4) Process for consideration of plant as new/existing (3.a.4) | RW | Covered in Meeting 5 presentation material. | Closed
21 | Website documentation and publishing format – can the documents run in chronological order or be split by meeting date? | SLK | SLK advised the current functionality of the website and workgroup pages does not permit this request however there is a review of National Grid's website being undertaken and these comments have been fed into this review. | Closed
22 | ‘Stakeholder Representation’ added as a standing agenda item for this workgroup | SLK | Complete. | Closed
23 | Corrections to Meeting 4 Presentations, publishing to website and notification to membership. | AJ and SLK | Complete. | Closed
24 | Additional post meeting action request from Mike Kay: Meeting invites to be sent for all forthcoming RfG workgroup meetings. | SLK | Complete. | Closed
25 | Future Compliance Regime Update | RM/JR | Taken forward from Action 5a, 5b and 9. There is the requirement for DECC and Ofgem to provide an update on the future compliance regime. For example, enforcement of G59 and G83, decommissioning, impact on domestic customers. 19.05.15 - An update will be given when the connections codes are more stable. 20.07.15 - Potential stakeholder workshop in the future to discuss options with stakeholders. | Ongoing
26 | Develop Risk Register draft for the RfG Workgroup | RW/AJ | To be covered in Meeting 6 presentation material (Agenda Item 9). Update 20.01.15 - Action closed and 'Risk Register' added as a Standing Agenda item. | Closed
27 | Project Plan Progression | Chair and Workgroup | To be covered in Meeting 6 presentation material (Agenda Item 8). Update 20.01.15 - Action closed and 'RfG Project Plan' added as a standing Agenda item. | Closed
28 | Banding Presentation Corrections/Updates | RW and RJW | Update banding presentation wording from ‘compromise’ to recommendation/proposal and include the suggestion from MB of clear splits between bands. Complete | Closed
29 | Costs to Generators. | CW, ZZ, KM (All) | Determine the cost to generators of complying with the cumulative requirements of bands A-C in particular and therefore the impact that would be felt in moving the thresholds. CW to progress this action for synchronous plant and RW to speak to Zoltan Zavody of Renewable UK for non-synchronous plant. To be covered in Meeting 6 presentation material (Agenda Item 6). Update 20.01.15 - RW liaising with Zoltan Zavody. Update 17.02.15 - ZZ and CW looking into with respective business areas (action owner change from RW to ZZ). 19.03.15 - AMPs shared findings with ZZ. ZZ to send indicative costs to RJW. KM to send through for Solar. Update 19.05.15 - AMPs have provided their stance on the Banding thresholds. Deadline suggested for next GC0048 Meeting 16 June 2015. This action has been moved to action 69 (Banding). | Closed
30 | Consideration of Operational costs to NGET | RW | To consider how to assess operational costs for NGET. To be covered in Meeting 6 presentation material (Agenda Item 7). Update 20.01.15 - Action to be closed as this will be covered in Meeting 7 (Agenda Item 6). | Closed
31 | Frequency Response Services | RW and MK | To consider how NGET will use frequency response services for Type B and C generators. MK will also look at commissioning costs and differences and update the work group. To be covered in Meeting 6 presentation material (Agenda items 7and 8). Update 20.01.15 - Discussions ongoing. AF and RW to cover in Meeting 7 (Agenda Item 5) and RW liaising with Adam Simms of NGET for potential to present at Meeting 8 in February. Update 17.02.15 - Meeting 8, Agenda Item 6 presentation by Adam Simms/Steve Lamb on developments in frequency response. MK to talk through any updates to commissioning costs action. Update 19.03.15 - Frequency Response Services part of this action is complete (covered in SL presentation and RJW Banding work). Workgroup suggested to keep open in light of Banding Work RJW is compiling and therefore this request has now been included in the overall banding action (no 69). | Close
32 | Preliminary banding assessment data source/s | RW and RJW | To provide more information on what data was used as part of the preliminary banding assessment including that from the GC0035 Workgroup and what the issues with this or necessary assumptions had been, and liaise with MK, AC and SM on any further information required from the DNOs. To be covered in Meeting 6 presentation material (Agenda Item 5). Update 20.01.15 - Discussions ongoing. RJW to provide progress update in Meeting 7 (Agenda item 6). Update 17.02.15 AND 19.03.15 - RJW to provide further update in March Meeting 9. Update 19.05.15 - Closed as action 63 covers all banding work. | Closed
33 | Presentation Correction | AJ and SLK | To update Timeline slide error – ‘general’ repeated twice and SLK to re-publish to the website (and advice the workgroup). Complete | Closed
34 | New Standing Agenda Item ' DECC/Ofgem Steering Group Reporting' | SLK | To add ‘DECC/Ofgem Steering Group Reporting’ as a standing agenda item. Complete | Closed
35 | DECC/Ofgem Steering Group Terms of Reference for workgroup circulation | JW | Complete. | Closed
36 | ‘RfG Banding Threshold Setting Considerations’ RW to circulate to the workgroup; assumptions and further details behind this presentations findings. | RW | Update 20.01.15 - RW to provide update in Meeting 7 (Agenda item 6). Update 17.02.15 - Action Complete | Closed
37 | RW and AJ to look into AF's query on what is the current maximum amount available of Frequency Response and also where possible add this to the graph slide 9 Projection of Generation Types by 2020 (Slow Progression model) detailed within the ‘RfG Banding Threshold Setting Considerations’ presentation. | RW and AJ | Update 20.01.15 - AF and RW will cover in Meeting 7 (Agenda Item 5). Update 17.02.15 - Action Complete | Closed
38 | RW to liaise with NGET System Operability Framework (SOF) representatives and the potential for them to give a presentation at a future RfG workgroup meeting. JW to speak to SO Ofgem colleagues for thoughts. | JW and RW | Update 20.01.15 - RW liaising with NGET SOF Team for potential presenting at future workgroup meeting. Update 17.02.15 - Meeting 8, Agenda Item 7 presentation by Ben Marshall on SOF. JW advised discussions ongoing internally and potential for Ofgem colleagues to attend the next workgroup meeting. Update 19.03.15 - JW has contacted SOF colleagues. RW has discussed with Ofgem. | Close
39 | RW/AJ and AF to look internally into the rationale behind the current GB banding (but noted they may not be able to confirm an answer on this). | AF, RW and AJ | Update 20.01.15 - AF email and conversations with workgroup following Meeting 6, AJ contacting SHE Transmission. Update from workgroup was the information provided to date was sufficient and therefore happy to close this action. | Closed
40 | RW and RJW to chase up non-synchronous banding data/costs from Renewable UK. | RW and RJW | Update 20.01.15 - Close as covered in Action 29. | Closed
41 | National Parameters Selection Presentation - AJ to provide workgroup with reasoning/values behind each parameter, any associated Grid Code modification names, confirmation of any impacts to the Project Plan timescale of 1 year and to review the TSO/DNO interactions. | AJ | Update 20.01.15 - Complete, update to work will be given at Meeting 7 (Agenda Item 7). Update 17.02.15 - Action Complete | Closed
42 | SLK to look into the possibility of circulating to the workgroup an organogram depicting the DECC/Ofgem Steering group placement in the ENC governance structure. | JW | Action with JW to look into internally. Update 20.01.15 - JW advised today's (20.01.15) JESG would be discussing the existing ENC Programme stakeholder groups for GB of which may see a change to the existing ENC Programme structure. JW to send round to the RfG Workgroup the outcome of these discussions. Update 17.02.15 - Closed SLK has sent onto the workgroup the new proposal paper discussed at JESG | Closed
43 | AJ/CR/All to work towards a detailed project plan by February 2015 ahead of the March Steering Group meeting. | AJ/CR/All | Update 20.01.15 - To be discussed further at Meeting 7. Update 17.02.15 - CR will discuss further at Meeting 8. Update 19.03.15 - Complete. | Close
44 | SLK to look to plan in future workgroup meetings from June 2015 onwards. | SLK | Update 17.02.15 - Action Complete | Closed
45 | SLK to check there are no future meeting date clashes with the RfG GC0048 workgroup and JESG and advise the workgroup accordingly. | SLK | Update 17.02.15 - Action Complete | Closed
46 | Workgroup members to draft potential questions for Adam Sims on future Frequency Response Capability ahead of inviting Adam to the next RfG workgroup meeting. | ALL | Update 17.02.15 - Action Complete | Closed
47 | Further to the above action, RW to also discuss with Adam Simms and NGET SOF Team the suggestion for a future position on the ‘current GB Frequency Response’ figures and for this to include demand side response. | RW | Update 17.02.15 - Meeting 8, Agenda Item 6 and 7 presentations by Ben Marshall and Adam Simms | Closed
48 | AJ and RJW to go through distinction of Power Park Module and Power Generating Module under RfG to determine compliance. | AJ & RW | Update 17.02.15 - AJ/RW to give update on 09.02.15 meeting. Update 19.03.15 - Complete. | Close
49 | MK, AC, SM and ZZ to assist RJW in profiling project connections of existing plant to confirm assumption one way or the other and to consider if there is an overwhelming rule of thumb regarding voltage/size that can be employed | MK, AC, SM, ZZ & RJW | Update 17.02.15 - Action Complete | Closed
50 | RJW to reconcile banding data against FES NGET predictions. | RJW | Update 17.02.15 - RJW will discuss further at March meeting 9. Update 19.03.15 -Will be addressed in RJW 'Draft Workgroup Consultation on RfG Banding Thresholds' paper covered under new action which is on Banding in general. | Close
51 | MK, DNOs (AC, SM) to look at banding data and see if there are any ‘uncertainties’ in their forecast. | MK, DNOs (AC, SM) | Updated 17.02.15 - Complete | Closed
52 | AJ to contact Solar Trade Association for potential attendance at future workgroup meetings | AJ | Update 17.02.15 - AJ has contacted the Solar Rep, they are currently looking at who would be best placed to attend on their behalf. Update 19.03.15 - Complete (Solar Representation present at Meeting 9). | Close
53 | SD to look at predicted demand vs generation profile and update the workgroup | SD | Update 17.02.15 - SD liaising with colleagues internally. Update 19.03.15 - No further information available for this, so nothing to add in from DECC. | Close
54 | CR to update project plan presentation for next workgroup. | CR | Update 17.02.15 - CR will discuss further at Meeting 8. Update 19.03.15 - Complete | Close
55 | Workgroup to review National Parameter information and provide by comments to AJ ahead of the next workgroup meeting | ALL | Update 17.02.15 - Action Complete | Closed
56 | SLK to check with JESG and ECCAF Secretariat for any documents which cover the existing list of legal and licence changes associated with the ENC implementation and a list of the existing RfG GB issues (Risk 14). | SLK | Update 17.02.15 - ECCAF Mapping has been sent onto the workgroup - Complete | Close
57 | JW to look into new nuclear Grid Code compliance. | RJW | Update 17.02.15 - RJW to move to Risk Register. | Closed
58 | RW to circulate to the workgroup an update on the Emergency & Restoration European Network Code and its interactions with RfG. | RW | Update 17.02.15 - Action Complete | Closed
59 | RW to circulate to the workgroup an update from David Spillet (Energy Networks Association) with regards to a Summary of standards IEC62786 and TS50549. | RW | Update 17.02.15 - Action Complete | Closed
58 | DS to speak to contacts for solar experts and SME manufacturers attendance at the GC0048 workgroup. RJW to draft an introductory note for DS to use with new contacts. | DS and RJW | Update 19.03.15 - Complete | Close
59 | JW to look at the FiT Register to identify if we have any missing representatives for the GC0048 Workgroup. | JW | Update 19.03.15 - JW advised the FIT register does not list any information on the manufacturers or installers of installations. JW has been in contact with Gemserv, who manages the MCS accreditation process (to get FIT funding your installation must be MSC accredited) and submitted the an information request to them. Update 19.05.15 - Closed action complete, Gemserv will also be advertising the GC0048 workgroup through their website and newsletter. | Closed
62 | RW and AJ to chase up ENTSO-E on their concern relating to the fault ride through parameters defined in Table 3.1 and 7.1. | RW and AJ | Update 19.03.15 - Chased and pursuing further. Complete. (GC0062 workgroup finalising - workgroup report in progress) | Closed
63 | NGET to look at agenda items for the next few meetings. | NGET | Update 19.03.15 - Complete, using the project plan and discussing at the start of each the meeting (meeting objectives). | Close
64 | SC and AJ to look to bring a draft of the mapping of definitions carried out so far and focus on the definitions for RfG vs Dcode. This is required for the next workgroup meeting and when appropriate this detail will be added into the project plan. | SC and AJ | Update 19.03.15 - Table produced and updated by AJ and SC . SC discussing at Meeting 9 . Update 19.05.15 - Closed SC has confirmed all required information has been received. | Closed
65 | RJW update the Risk Register; i. New column for ‘risk rating after proposed mitigation’ ii. Review ‘Issues’ tab and seek to change to ‘points to note’. iii. Add ‘Stakeholder Engagement’ risk to the Risk Register to make sure we are capturing all stakeholders. | RJW | Update 19.03.15 - Complete | Close
66 | RM and CR to liaise on the Project Plan – CR to develop and arrange TCON with RM. | RM and CR | Update 19.03.15 - Complete | Close
67 | SLK to pass on minutes for the DECC/Ofgem Stakeholder Meeting held on the 19 February. | SLK | Update 19.03.15 - Complete | Close
68 | Dcode/RfG Mapping; i. Workgroup to provide comments on the Document (i) to sarah.carter@ricardo.com by Tuesday 14 April. ii. SC to discuss proposed approach to Dcode/RfG Mapping at JESG on 28 April. iii. Dcode/RfG Mapping to be approved by GCRP and DCRP. iv. Dcode/RfG Mapping to be sent to the DECC/Ofgem Steering Group for approval. v. Ofgem to look into legal requirements in relation to DSO/DNO references presence in RfG and how to take this forward with RfG mapping (as referred to in SC Presentation). | SC and All | Update 19.05.15 (i) Complete (ii) Complete (ii, iii, iv) Complete: MK will provide an update under agenda item 5 of Mays GC0048 meeting. (v) Complete: RM advised legally, DSO is broader than what we use at the moment 'DNO', DSO will not overwrite the DNO, and DNO should not be an issue for us to use unless our Member State (DECC) advises us to define DNO as DSO. Therefore at the moment DNO until advised otherwise. | Closed
69 | RfG Banding Thresholds and Data Collection; i. Finalise Generators Costs – CM, CW, JAT, ZZ, JD, CMd, KM ii. RJW to send Solar template for costs to KM, KM to compile costs and return to RJW. iii. RJW to include FES information, peak and minimum demand for a year, required reserve and response and how this changes over time. iv. Frequency Response Services, in conjunction with iii. v. Following queries raised by the workgroup on FES Scenarios data, RJW to return to the August workgroup with updates on; National Demand vs Connected Generation (banding insight), the time horizon for banding setting and the specifics behind the FES data as queried by the workgroup. | RJW and All | Update 20.07.15 further discussion at July GC0048 workgroup meeting. (i) Ongoing (ii) Ongoing (iii) Ongoing (iv) Ongoing (v) NEW | Ongoing
70 | RM to discuss with CR legal requirements and how reference in the RfG project plan. | RM and CR | Update 19.05.15 - Complete | Closed
71 | RW to write to JESG chair for advise as to approach for Grid Connections implementation groups, this is also added as a DECC/Ofgem Steering Group item for progression as this is the usual route for such queries. | RW | Update 19.05.15 - Complete | Closed
72 | Workgroup to provide comments to RJW on Banding Thresholds workgroup report. New separate action (prev. in 69). | All | Update 19.05.15 - Complete | Closed
73 | Update workgroup on approach taken for HVDC and DCC stakeholder engagement and implementation (following May JESG) | Ofgem and DECC | 20.07.15 - Outcome of GCRP. GCRP approved approach. DCC will betaken to DCRP in for comment/approval. Further communications through the JESG. Both workgroups will be set up and there will be coordination between RFG, DCC and HVDC workgroups. | Close
74 | Workgroup to send any comments to MK and RW on the guidance on implementation paper. | All | 20.07.15 - Any further comments to be sent on ahead of next workgroup meeting (August GC0048) | Close
75 | Workgroup to send any comments on the RfG Mapping exercise template to RW ahead of the next GC0048 meeting on 16 June. (Mapping exercise to take place in July - 20-21 provisionally booked pending RfG vote in June). | All | 20.07.15 - Complete. | Close
76 | CR to circulate project plan and scope for modifications to the workgroup. | All | 20.07.15 - Complete. | Close
77 | Circulate banding presentation and FES link to the workgroup. | SLK |  | NEW
78 | Circulate ENTSO-E information on the RfG Implementation Workshop | SLK |  | NEW
79 | Include the Risks mentioned today in relation to coordination across the ENCs and Coordination across the Connection Codes and the implementation workgroups | RJW |  | NEW