## Timeline for approval
Section 8: 8.19.1.(e) makes the following provision for the Panel and states “Having regard to the complexity, importance and urgency of particular CUSC Modification Proposals, the CUSC Modifications Panel may determine the priority of CUSC Modification Proposals and may (subject to any objection from the Authority taking into account all those issues) adjust the priority of the relevant CUSC Modification Proposal accordingly”
Complexity | The modification is viewed as being resource intensive and will most likely require a higher than average number of workgroups to conclude the process. Additionally the modification defect is viewed to have implications for many different areas of the energy market which need to be taken into consideration throughout the process.
Importance | The perceived value & risk associated with the proposed modification. The value / risk could be considered from a number of different perspectives i.e. financial / regulatory / licence obligations both directly for customer and end consumers more generally.
Urgency | A modification which requires speedy consideration within the code governance process, both complexity and importance should be factors considered in evaluating urgency as well as the timescales for implementation within the respective code.
Movement | Date Modification Raised | Modifications at WG Stage | Panel Comments on Prioritisation | Cross Code Impacts | Date of First WG | WG Development [WG already held] | WG Report submission | Expected FMR Date to Authority | Anticipated frequency of meetings*
GC0104: EU Connection Codes GB Implementation – Demand Connection Code
NEW | 2019-05-22 | CMP317 Identification and exclusion of Assets Required for Connection when setting Generator Transmission Network Use of System (TNUoS) charges | Based on current assumption on timing with 2020 deadline; if it is assessed that the timing is not so critical the modification will be reviewed and may be reassessed on the prioritisation stack. |  | TBC | TBC | TBC | TBC | TBC
Same position | 2018-04-27 | CMP295 ‘Contractual Arrangements for Virtual Lead Parties (Project TERRE)’ | Prioritisation based on alignment to European Law changes/timetables; requirement for decision by April |  | 12 July 2018 | [3] up to March 2019 | Timeline agreed: May 2019 | July 2019 | TBC
Same position | 2019-02-15 | CMP311 'Reassessment of CUSC credit requirements for Suppliers, specifically for “User Allowed Credit” as defined in Section 3, Part III section 3.27 of the CUSC' | Priority based on substantial changes for Suppliers and Consumers. Early conculsion will help parties to understand any requirements on them |  | TBC | TBC | TBC | TBC | TBC
Moved up one | 2017-06-22 | CMP280 ‘Creation of a New Generator TNUoS Demand Tariff which Removes Liability for TNUoS Demand Residual Charges from Generation and Storage Users & CMP281 ‘Removal of BSUoS Charges From Energy Taken From the National Grid System by Storage Facilities' | High Priority because of clear impact for users and a known policy issue. Complexity of alternative (raised during WG Consultation) has resulted in an extended timeline to October. | Yes | 4 August 2017 | [16] up to April 2019 | Timeline agreed: June 2019 | August 2019 | TBC
Moved down one | 15/02/2018 | CMP291 ‘The open, transparent, non-discriminatory and timely publication of the harmonised rules for grid connection (in accordance with the RfG, DCC and HVDC) and the harmonised rules on system operation (in accordance with the SOGL) set out within the Bilateral Agreement(s) exhibited in the CUSC.’ | Prioritisation based on alignment to European Law changes/timetables |  | 12 July 2018 | [2] up to December 2018 | Timeline agreed: August 2019 | October 2019 | TBC
Same position | 2018-10-19 | CMP308 Removal of BSUoS charges from Generation | High impact of BSUoS Payers, Impact on BSUoS recovery, Consumer Impacts |  | 18 December 2018 | 4 up to April 2019 | Timeline agreed: June 2019 | August 2019 | TBC
NEW | 2019-04-16 | CMP315 - TNUoS: Review of the expansion constant and the elements of the transmission system charged for | Scale and complexity; no requirement with compliance. Unlikely to be implemented ahead of Tariff setting for 2020. To be reviewed follwowing first workgroup |  | TBC | TBC | TBC | TBC | TBC
NEW | 2019-04-16 | CMP316 - TNUoS Arrangements for Co-located Generation Sites | Scale and complexity; no requirement with compliance. Unlikely to be implemented ahead of Tariff setting for 2020. To be reviewed follwowing first workgroup |  | TBC | TBC | TBC | TBC | TBC
Moved down one | 2017-10-10 | CMP287 ‘Improving TNUoS Predictability through Increased Notice of Inputs Used in the TNUoS Tariff Setting Process’ | Priority based on a need for a quick decision date to have an effect on tariff setting timetables |  | 18 January 2018 | [5] up to October 2018 | Timeline agreed: July 2019 | September 2019 | TBC
Same position | 2017-10-10 | CMP286 ‘Improving TNUoS Predictability through Increased Notice of the Target Revenue used in the TNUoS Tariff Setting Process’ | Priority based on a need for a quick decision date to have an effect on tariff setting timetables |  | 18 January 2018 | [5] up to October 2018 | Timeline agreed: August 2019 | October 2019 | TBC
Same position | 2018-02-12 | CMP288’ Explicit Charging Arrangements for Customer Delays’ and CMP289’ Consequential change to support the introduction of explicit charging arrangements for customer delays and backfeeds via CMP288’ | Priority based on Consumer benefits. Quite a degree of complexity involved, extended timeline to December2018. |  | 16 May 2018 | [5] up to December 2018 | Timeline agreed: May 2019 | July 2019 | TBC
Same position | 2018-08-23 | CMP304 'Improving the Enhanced Reactive Power Service by making it fit for purpose' | High Materiality |  | TBC | [2] to November 2018 | TBC | TBC | TBC
Same position | 2018-04-23 | CMP298 - Updating the Statement of Works process to facilitate aggregated assessment of relevant and collectively relevant embedded generation | Priority based on assessment against other modifications. A SOW process is also already in place, so there is no immediate need for any urgency. |  | 02 October 2018 | [1] September 2018 - January 2019 | Proposed: TBC | Proposed: TBC | TBC
Same position | 2018-09-20 | CMP306 - Align annual connection charge rate of return at CUSC 14.3.21 to price control cost of capital | Materiality, Clear solution, Link to having a decision by Autumn 2019 to give time for consideration in regards to publication of charging statement. |  | 31 January 2019 | 2 up to April 2019 | TBC | TBC | TBC
Same position | 2018-02-15 | CMP292 ‘Introducing a Section 8 cut-off date for changes to the Charging Methodologies | Priority based on when a decision will be needed for the tariff setting process |  | 02 October 2018 | September 2018 - January 2019 | Proposed: May 2019 | Proposed: July 2019 | TBC
Same position | 2018-06-27 | CMP300 'Cost reflective Response Energy Payment for Generators with low or negative marginal costs' | Low materiality |  | 15 February 2019 | September 2018 - January 2019 | Proposed: June 2019 | Proposed: August 2019 | TBC
Modifications on hold
CMP271 - Improving the cost reflectivity of demand tx charges (RWE) CMP274 - Winter TNUoS Time of Use Tariff for Demand TNUoS (UK Power Reserve) CMP276 – Socialising T costs associated with “green policies” (Alkane) CMP307 - Expanding the BSUoS charging base to include embedded generation
Modifications not at workgroup
Modification number |  | Next Stage Gate | Anticipated date
CMP285 ‘CUSC Governance Reform – Levelling the Playing Field’ |  | Panel vote | TBC
CMP301 - Clarification on the treatment of project costs associated with HVDC and subsea circuits |  | Authority decsion | TBC
CMP305 - Removal of the Enhanced Reactive Power Service (ERPS) |  | Code Admin Consultation | 2019-06-01
CMP309 - CUSC changes in the event the UK leaves the EU without an agreement |  | DFMR | TBC
CMP310- CUSC section 14 changes in the event the UK leaves the EU without an agreement |  | DFMR | TBC
CMP313 - Critical Friend review period for submission of new modifications |  | Code Admin Consultation | Closes 14/05/2019
CMP303 'Improving local circuit charge cost-reflectivity' |  | Authority decsion | TBC
CMP314- Updating the CUSC to align Power Available with the Grid Code definition for Power Park Modules |  | Code Admin Consultation | TBC
*Frequency of meetings is dependent on consultation phases, workgroup availability, CA availability
#VALUE!
Down 3
Down 2

## Sheet2
July |  |  | Suggestions to add onto Prioritisation stack next time:
| WG Meetings | CMP293/94 WebEx 09/07/2018 | * Plan on a page
|  | CMP291/95 12/07/2018 | * Add CMP300
CMP288/89 16/07/2018
CMP285 17/07/2018
CMP280/81 26/07/2018
CMP286/87 - Planned for 6th July, postponed to carry out analysis to the 31st July
| CAC | CMP301 sent out 02/07/2018
| WG Consultation | CMP280 closed 10/07/2018
| Panel Recommendation Vote | DFMR CMP301
DFMR CMP275/CMP296/CMP297/CMP299
| Sent FMR's to Authority | 4 =CMP275, CMP296, CMP297 & CMP299
Aug | WG Meetings | CMP288/89 6/08/2018
CMP291/95 TBC
CMP280/81 TBC - Last week of August
| WG Consultation (hoping to send out) | CMP285 and CMP281
Sep | WG Meetings | CMP291/95 TBC
CMP292 TBC
CMP298 TBC
CMP300 TBC