## CUSC Prioritisation
CUSC - Prioritisation Stack
Mod Number | Panel Comments on Prioritisation as at 30 September 2022 | Proposer Organisation | Title
High - note that the Modifications are listed in numerical order and are not in priority order within this priority category
CMP315 and CMP375 | • Panel recognised there is a material impact here; however, argued that need to understand the TCR outcome before progressing further This was de-prioritised by Panel whilst the Modifications to address Ofgem's Targeted Charging Review decision were being progressed. November 2020 Panel agreed to move CMP315 from “Low to Medium” to “High” in light of recent developments re: the Expansion Constant. ESO's modification re: the wider solution on the Expansion Constant (CMP375) was presented to the June 2021 Panel. Panel agreed that CMP315 will be progressed in parallel with CMP375 (rather than be formally amalgamated) with Workgroups on the same day. Panel noted that CMP375 is a complex change and agreed that it is better to commence this as soon as possible and provide clarity for stakeholders on the future of the Expansion Constant and placed this “High” in the prioritisation stack. Given the interaction with CMP315, CMP315 will remain high in the prioritisation stack. Workgroups recommenced on 10 August 2021. | PeakGen (CMP315) ESO (CMP375) | TNUoS: Review of the expansion constant and the elements of the transmission system charged for (CMP315) Enduring Expansion Constant & Expansion Factor Review (CMP375)
CMP328 | • Raised on behalf of all DNOs • Needs to be progressed in parallel with completion of Transmission and Distribution interactivity process (expected to be completed ~ April 2021) • Significant volumes of these Tertiary Windows connections already progressing so there is a pressing need for a solution Panel have previously expressed concern on the direction of travel; however October Panel noted recent progress made and re-assessed priority at November Panel following the Workgroup on 19 November 2020. The Panel noted the complexity of CMP328 and the need for one more Workgroup in January 2021 prior to the Workgroup Consultation being issued. The November 2020 Panel were content to defer the decision on CMP328 until January 2021 Panel with the expectation that the Workgroup Consultation had been issued by then. However, as the Workgroup has been delayed at Proposer's request to 10 February 2021, Code Admin proposed that the decision on CMP328 prioritisation was deferred until February 2021 Panel. Panel agreed to this request. February 2021 noted that Workgroup Consultation was issued on 19 February 2021 and left priority unchanged. | Scottish and Southern Energy Power Distribution Limited | Connections Triggering Distribution Impact Assessment
Medium to High - note that the Modifications are listed in numerical order and are not in priority order within this priority category
CMP330/CMP374 | • Simple change and potential for cost savings and faster connections • Clarity needed ahead of Contracts for Difference Auctions This was de-prioritised by Panel whilst the Modifications to address Ofgem's Targeted Charging Review decision were being progressed). At June 2020 Panel, Panel determined that the priority of this was Medium to High. | Energy Potential Limited | Allowing new Transmission Connected parties to build Connection Assets greater than 2km in length
CMP344 | At June 2020 Panel, Panel determined that the priority of this was High. Final Modification Report was sent to Ofgem on 12 January 2021 requesting a decision by 25 January 2021 to meet an Implementation Date of 1 April 2021. However, Ofgem advised they were unable to make a decision by 25 January 2021 and sent back CMP344 on 5 May 2021 as they required further clarity on which OFTO costs the Proposal applies to and they need quantitative information regarding how the change impacts each set of network users. May 2021 Panel agreed for the Workgroup to be re-formed to address each of Ofgem's concerns and agreed in principle (following the assessment by the Workgroup) that a Code Administrator Consultation is needed to be run before it is re-presented to Panel for Recommendation Vote). They also agreed to place this as Medium to High in the prioritisation stack. | RWE | Clarification of Transmission Licensee revenue recovery and the treatment of revenue adjustments in the Charging Methodology
CMP376 | July 2021 Panel placed this as "Medium to High" in the prioritisation stack. Panel noted the high materiality and there a number of unanswered questions, which a CUSC Workgroup will need to address. Given the extensive work already done on "Queue Management" and that the process will be used across industry imminently, the July 2021 Panel agreed that this should be progressed sooner rather than later. At February 2022 Panel, Code Admin advised that the CMP376 Workgroup on 28 February 2022 had been postponed as the Workgroup had provided extensive feedback particularly on the practicality of the proposed milestones that needed to be considered further by the ESO Connections team. CUSC Panel were advised that it was prudent to postpone Workgroups will be paused until September 2022 to allow the ESO Connections team to fully take into account the feedback received and ensure the solution had been fully thought through. Despite this “pause”, Panel agreed that this still “Medium to High” in the prioritisation stack. Workgroups restarting 6 September 2022. | ESO | Inclusion of Queue Management process within the CUSC
CMP396 | August 2022 Panel placed as “Medium to High” in the prioritisation stack because there appears to be direct impact on competition and the end consumer. However, the Panel agreed that independent legal advice needs to be commissioned first as important to determine whether or not this proposed change is legally permissible. Panel also set a revised Terms of Reference on this basis and requested that the 1st Workgroup develop and agree the request for legal opinion which would then be issued to an independent QC. Once the QC opinion has been finalised, this will be issued to Panel, who would then revise Terms of Reference and review current “Medium to High” priority | Saltend Cogeneration Company Ltd | Re-introduction Of BSUoS on Interconnector Lead Parties
CMP398 | September 2002 Panel placed as “Medium to High” in the prioritisation stack due to the alignment with GC0156: Facilitating the Implementation of the Electricity System Restoration Standard. | SSE Generation Ltd | GC0156 Cost Recovery mechanism for CUSC Parties
Medium - note that the Modifications are listed in numerical order and are not in priority order within this priority category
CMP304 | • Modification seeks to apply a different timescale to the provision on reactive power – Panel divided though on whether this is a simple change as solution still needs to be clarified • Ofgem cannot make a final decision on CMP305 until CMP304 is completed • Decreased cost to consumers if more competition This was de-prioritised by Panel whilst the Modifications to address Ofgem's Targeted Charging Review decision were being progressed. Workgroups recommenced on 8 November 2021. Prioritisation was discussed at August 2022 Panel but was not changed. Proposer is content to wait for ~ 2 months whilst the ESO team who are leading on the Reactive Reform (Market Design) project finalise their conclusions but would be keen to restart Workgroups if conclusions are not to be reached in the foreseeable future. | SSE Generation | Improving the Enhanced Reactive Power Service by making it fit for purpose
CMP392 | Panel agreed that CMP392 will be placed as “Medium” in the prioritisation stack noting there is a potential compliance risk but some Panel Members argued that materiality is low and therefore on balance agreed a "Medium" priority. | SSE Generation | Transparency and legal certainty as to the calculation of TNUoS in conformance with the Limiting Regulation
CMP393 | Panel agreed that CMP393 will be placed as “Medium” in the prioritisation stack as although there could be a high materiality and complexity (given the analysis required), some Panel Members noted it may be prudent to wait for the TNUoS Taskforce to meet and agree high-level principles. On balance, Panel agreed a "Medium" priority. CMP393 and CMP394 will be run on the same day initially. | Zenobe | Using Imports and Exports to Calculate Annual Load Factor for Electricity Storage
CMP394 | Panel agreed that CMP394 will be placed as “Medium” in the prioritisation stack as although there could be a high materiality and complexity (given the analysis required), some Panel Members noted it may be prudent to wait for the TNUoS Taskforce to meet and agree high-level principles. On balance, Panel agreed a "Medium" priority. CMP393 and CMP394 will be run on the same day initially. | Zenobe | Removing Generation Charges from Electricity Storage Operators in Positive TNUoS Zones
Low to Medium - note that the Modifications are listed in numerical order and are not in priority order within this priority category
CMP331 | • April 2022 Implementation at earliest • Materiality on the wider charging base not clear This was de-prioritised by Panel whilst the Modifications to address Ofgem's Targeted Charging Review decision were being progressed. At June 2020 Panel, Panel determined that the priority of this was Low. At the quarterly prioritisation deep-dive (at Panels on 29 October 2021 and 26 January 2022), no case was presented to change the priority; however, Code Admin have discussed numbers and content of Workgroups required with the Proposer and from that have built an indicative timeline to progress this change. Panel on 29 April 2022 agreed for the priority to move from "Low" to "Low to Medium" on the basis that this has become more pressing for potential new connectees. | Energy Potential Limited | Option to replace generic Annual Load Factors (ALFs) with site specific ALFs
CMP379 | September 2021 Panel placed this as "Low to Medium" in the prioritisation stack as they considered this has a low materiality and a decision is not needed until end December 2022 (now November 2023) | ESO | Determining TNUoS demand zones for transmission-connected demand at sites with multiple Distribution Network Operators (DNOs)
Low - note that the Modifications are listed in numerical order and are not in priority order within this priority category
CMP291 | • Complex change • Enduring requirement but no compliance date set This was de-prioritised by Panel whilst the Modifications to address Ofgem's Targeted Charging Review decision were being progressed. At June 2020 Panel, Panel determined that the priority of this was Low. At June 2021 Panel, Panel discussed the interaction with GC0117 and Code Admin confirmed with the Grid Code Review Panel ESO representative confirmed that progression of GC0117 is not dependent on CMP291 progressing . Therefore, CMP291 will remain “Low” in the prioritisation stack. At the last quarterly prioritisation deep-dive (August 2022 Panel), no case was presented to change the priority. | SSE Generation | The open, transparent, non discriminatory and timely publication of the harmonised rules for grid connection (in accordance with the RfG, DCC and HVDC) and the harmonised rules on system operation set out within the Bilateral Agreements
CMP341 | • Complex • Although a CACOP and Ofgem driven initiative, there does not appear to be any current industry appetite to progress This was de-prioritised by Panel whilst the Modifications to address Ofgem's Targeted Charging Review decision were being progressed. At June 2020 Panel, Panel determined that the priority of this was Low. At the last quarterly prioritisation deep-dive (August 2022 Panel), no case was presented to change the priority. | ESO | CUSC Sandbox: enabling derogation from certain obligations to support small-scale trials of innovative propositions
CUSC Prioritisation Criteria
Section 8: 8.19.1.(e) makes the following provision for the Panel and states “Having regard to the complexity, importance and urgency of particular CUSC Modification Proposals, the CUSC Modifications Panel may determine the priority of CUSC Modification Proposals and may (subject to any objection from the Authority taking into account all those issues) adjust the priority of the relevant CUSC Modification Proposal accordingly”
Complexity | The modification is viewed as being resource intensive and will most likely require a higher than average number of workgroups to conclude the process. Additionally, the modification defect is viewed to have implications for many different areas of the energy market which need to be taken into consideration throughout the process.
Importance | The perceived value & risk associated with the proposed modification. The value / risk could be considered from a number of different perspectives i.e. financial / regulatory / licence obligations both directly for customer and end consumers more generally.
Urgency | A modification which requires speedy consideration within the code governance process, both complexity and importance should be factors considered in evaluating urgency as well as the timescales for implementation within the respective code.